## Tasks
TASK NAME | SUB-TASKS | COMMENTS | STATUS | ASSIGNED TO | START DATE | END DATE | PRIORITY
UI Design | User Login |  |  | Youming | Teaching Break | 2022.4.25(W7) | 1
| User Info |  |  | Youming | Teaching Break | 2022.4.25(W7) | 1
| Post Creation |  |  | Youming | 2022.4.26 | 2022.5.4(W9) | 3
| Sports Creation |  |  | Youming | 2022.4.25 | 2022.4.28(W8) | 2
| Sports Map Page |  |  | Youming | 2022.4.25 | 2022.4.28(W8) | 2
| Sports List |  |  | Youming | 2022.4.25 | 2022.4.28(W8) | 2
Testing
User | Login |  | In Progress | Jie Song | 2022.4.19 | 2022.4.22(W7) | 1
| Register |  | Not Started | Jie Song | 2022.4.19 | 2022.4.22(W7) | 1
| User Search |  |  | Jie Song | 2022.4.19 | 2022.4.22(W7) | 1
| Follow |  |  | Jie Song | 2022.4.19 | 2022.4.22(W7) | 1
Testing
Post | Post Creation |  |  | Jie Song | 2022.4.25 | 2022.5.4(W9) | 3
| Post Deletion |  |  | Jie Song | 2022.4.25 | 2022.5.4(W9) | 3
| Post Edit |  |  | Jie Song | 2022.4.25 | 2022.5.4(W9) | 3
| Post Search |  |  | Jie Song | 2022.4.25 | 2022.5.4(W9) | 3
Testing
Sport Activity | Activity Creation |  |  | Xu | 2022.4.19 | 2022.5.4(W9) | 3
| Activity Edit |  |  | Xu | 2022.4.19 | 2022.5.4(W9) | 3
| Activity Deletion |  |  | Xu | 2022.4.19 | 2022.5.4(W9) | 3
| Activity Search |  |  | Xu | 2022.4.19 | 2022.5.4(W9) | 3
Testing
Utils | JsonUtil | transform between Json and Object | Complete | Jie Song | 2022.4.19 | 2022.4.22(W7) | 2
| FileUtil | Read and Write File | In Progress | Jie Song | 2022.4.20 | 2022.4.22(W7) | 2
| Token/Parsing |  |  | All
Testing
Data Structure | RedBlack（Insert, Search) |  |  | Ke | 2022.4.25 | 2022.4.28(W8) | 1
| Testing |  |  | Ke |  |  | 1
DAO |  |  |  | JIE，Xu |  | 2022.4.22(W7) | 1
Notification | User |  |  | All |  |  | 3
| Post |  |  | All |  |  | 3
| Sport Activity |  |  | All |  |  | 3
Testing